## Slide 1
Engagement Management Add-On Process
RealPage Philippines

## Slide 2
New Logo vs Expansion vs Add-on
New Logo
A customer that is completely new to RealPage and has not previously licensed or utilized any RealPage products or services.
Expansion
An existing RealPage client (Property Management Company) that is adopting an additional solution for the first time, expanding beyond their currently licensed products.
Add-On
An existing RealPage client that already licenses a specific product and is extending its use by onboarding additional properties or sites to that same solution.
Add-On with Expansion
An existing RealPage client that is both expanding usage of an existing product to additional properties while also implementing a new solution for the first time.

## Slide 3
CATEGORY | NEW LOGO | ADD-ONS | EXPANSION
CLIENT TYPE | New to RealPage | Existing client | Existing client
SCOPE | Initial Platform adoption | New property with same or smaller product stack | Adding new products or solutions
CONSULTING ORDERS | Required | Usually not required | Required
DISCOVERY CALLS | Yes | Typically not needed | Yes
ADOPTION MILESTONES | Yes | No | Yes
CLIENT SUPPORT LEVEL | High touch | Typically Low Touch | High/Medium Touch
TRAINING / WORKSHOPS | Almost always needed | If needed | Highly Recommended
DELIVERABLES | Heavy lift | Lighter; can mirror other sites | Heavy lift
TIMELINE | Longer | Faster (sometimes ASAP) | Depends on number of products and site
New Logo vs Expansion vs
Add-On​

## Slide 4
Add-On Journey
  New Project Assignment​
  Research
  Introduction
  Data Collection
  Scheduling Implementations​
  Issues, Questions. Escalations​
  End of Engagement

## Slide 5
New Project Assignment
  Your manager informs you of a new assignment​
  You receive an email from RealPageEngaged​***
  Your current PMC informs you of a new acquisition​
  You takeover a project from another EM/EC

## Slide 6
PMC & Order
Review (Research)
  Signed order forms
    Watch out for consulting orders
    Determine assignment timelines
  SALESFORCE
  Order Request
    details, chatter, revisions​
  Property Implementation Orders
  Backlog Report
  Create/Update project tracker
  Review order history check for any ‘missing’ products​
  DATAHUB Questionnaires
Review Orders
  Get insights from previous EM
  Connect with your Sales Rep – Sales prep email template/call
  Review PMC account page in Salesforce
  Review ongoing email threads with scheduling or sales
Get to know your client
  Conversion may be scheduled before you get assigned
  Check CSR (Conversion Service Request) in the Property Page
  Determine assigned IA (Implementation Analyst)
  Reach out to IA to loop you in on all emails
RP CONVERSIONS

## Slide 7
EC Intro
  Scheduling team will introduce you to the client
  KO Email Template
  Always include Sales Rep
  Offer a KO meeting
Kick off Email
  Client POC
  Takeover Date
  Vacant or with Residents
  Client timeline (asap, long term)
  Priority Solutions
Important Information Relevant to Implementations

## Slide 8
Kickoff Meeting
  Introduce yourself and your role​
  Discuss project plan
Introduction
  Determine takeover/closing date​
  Schedule conversion​
  You can obtain available conversion schedules prior to the call​
  Take note of schedules that have limited slots
Conversion
  Discuss product dependencies and timelines​
  Discuss deliverables needed and provide due dates​
  Check for any missing orders
Ancillary Products
  Quick demo if needed​
  Set the due dates in datahub
DataHub
  If consulting is needed set expectations on assignment wait time​
Consulting Assignment Timelines
  Schedule recurring calls/emails
Weekly Updates

## Slide 9
Data Collection and
Scheduling Implementations
  Reach out to scheduling team to schedule conversion/migration and push orders​
  Add Due Dates in DataHub based on agreed timelines with the clients​
  Align with Solution Consultants on Deliverables and Timelines:
    Provide client target dates
    Update on status of deliverables
    Monitor progress
    Follow up... Follow up.. Follow up..

## Slide 10
OneSite Conversion
Ask the client to notify you once they have completed their conversion – this would also be your OneSite go live date
Self-Start Conversion
  RP Migrations will send a KO email before their scheduled conversion (1-2 weeks)
  Take note of deadlines, make sure client is aware, follow up if needed​
  Data Validation – 1st 3 days of conversion schedule (Crucial)
  Once data is validated it will be checked in for conversion and conversion completion date will be provided.​
  Conversion team may still reach out to client for additional questions
RP assisted Conversion/Transfer

## Slide 11
Ancillary Products
  Once OneSite go live date is determined you can work on scheduling the ancillary products​
  Important: implementation timelines and product dependencies​
  Monitor deliverables completion
  Most products use DataHub, a few exemptions
    G5 Website > Onboarder
  Monitor orders status in SalesForce.
    Implementation Comments
    Backlog Reason
    Implementation Items
  Activation Emails

## Slide 12
Issues, Questions, Escalations
  Reach out to the assigned SC if client has any product-related questions and any issues reported after go live. Schedule calls if needed​.
  Any client escalations or possible client escalations –notify your manager right away. ​
  Follow proper escalation path if SC is unresponsive or is unable to follow agreed Go Live date.

## Slide 13
End of Engagement
  Half-way through the project start notifying your clients of your impending end of engagement​
  2 weeks prior to intended EOE, send an EOE notice to your client
    Give a summary of what is pending
    Ask for upcoming properties
  Notify SCs and Sales Rep of upcoming EOE.
    Cover all pending implementations
  Send your End of Engagement email

## Slide 14
Add-On Challenges
  Time Sensitivity/ Client Demands​
  Planning go-live dates​
  Clients have different processes​
  Incorrect or Missing Orders​
  Consulting Assignment Wait Time​
  New POC/Staff​
  Product Specific Questions – who should answer?​
  Issues/Questions involving multiple products​
  No Consultant - will need support ticket​
  Questions on deliverables

## Slide 15
Engagement Management
Professional Services Group
Thank You
Very Much