## Slide 1
PH Engagement Coordinator
Product dependency
workflow
How to sequence setup, activation, go-live, and integrations across the product ecosystem.
OneSite
the core product
SET UP EARLY
ACTIVATE AFTER ONESITE
Use this workflow to build realistic implementation timelines and avoid sequencing risks.
Engagement Coordinator Training
01

## Slide 2
01 / THE RULE
Separate setup from activation
A product may be prepared early even when its activation depends on another product.
1
Prepare
Configuration, data gathering, and readiness work can begin.
→
2
Activate
The product becomes usable once its required dependency is live.
→
3
Integrate
Connect the product to OneSite or other required products.
Coordinator mindset
Always ask: “Can we set it up now?” and “What must be live before we activate it?”
Engagement Coordinator Training
02

## Slide 3
02 / BEFORE ONESITE
Use the early window for parallel work
These products can move forward while the OneSite timeline is still being finalized.
Accounting Entity
Create anytime → integrate with OneSite
Payments
Setup can begin early → activate after OneSite is live
Knock
Can go live early → integrate with OneSite later
Website
Set up early → complete integrations later
Contact Center Answer Automation
Can go live prior to OneSite
eSupply
No product dependencies → go live anytime
Key watch-out: early setup does not automatically mean early activation.
Engagement Coordinator Training
03

## Slide 4
03 / ONESITE MILESTONE
OneSite unlocks the main go-live cluster
Schedule the products below with OneSite and confirm their readiness criteria before launch.
ODEs + SDEs
Go live with OneSite
Facilities
Go live with OneSite
Maintenance Management
Go live with OneSite
Screening
Go live with OneSite
Screening readiness gate
Identify a property whose screening scoring model can be mirrored before scheduling the go-live.
Engagement Coordinator Training
04

## Slide 5
04 / PAYMENTS PATH
Payments can be prepared early—but activation waits for OneSite
This is the most important sequencing distinction for resident-facing functionality.
1
Payments setup
May begin early
→
2
OneSite live
Required activation gate
→
3
Payments activated
Online payment capability enabled
→
4
Loft Leasing live
Requires activated Payments
Loft Living note
Loft Living requires OneSite and may go live before Payments. Residents cannot pay online until Payments is activated.
Engagement Coordinator Training
05

## Slide 6
05 / POST-ONESITE SEQUENCING
Once OneSite is live, activate the next layer in order
Use the dependency, not the preferred date, as the scheduling rule.
Loft Living
OneSite
Online Renewals
OneSite
Syndication
OneSite
Business Intelligence
OneSite + current property date
Performance Analytics
OneSite + current property date
After Payments is activated
•
Loft Leasing can go live.
•
Loft Loyalty and Loft Moving go live 3–5 days after Loft Living.
•
The 3–5 day timing still requires Payments to be live.
Engagement Coordinator Training
06

## Slide 7
06 / INTEGRATIONS AND ANALYTICS
Finish the timeline with integration gates
Some products can be live early but are not complete until the required connections are in place.
Website
Setup early
Final integration after all are live:
•
OneSite
•
Loft Living
•
Loft Leasing
•
Knock
BI + Performance Analytics
Setup begins only when:
•
OneSite is live
•
The property date is current
Can not start setup before both gates are met.
Engagement Coordinator Training
07

## Slide 8
07 / APPLY THE WORKFLOW
Coordinator checklist
Use these questions before confirming an implementation or go-live date.
✓
What can be set up in parallel before OneSite?
✓
Is OneSite live before activating Payments?
✓
Has the Screening scoring-model property been identified?
✓
Is Payments activated before Loft Leasing?
✓
Are Loft Loyalty and Loft Moving scheduled 3–5 days after Loft Living?
✓
Is the property date current before BI or Performance Analytics setup?
✓
Are all Website integration prerequisites live?
Outcome: a timeline that is executable, dependency-aware, and clear to the customer and internal teams.
Engagement Coordinator Training
08